## Threat Map
Church Machine (CTMM) vs W7 / Scheme 48 — adversarial test plan for W7 open threats
Source of threats: J. Rees, 'A Security Kernel Based on the Lambda-Calculus', MIT AI Memo 1564 (1996). CTMM mechanisms from ratified design notes; rows marked 'Unknown' or 'Inferred' are Claude's inference, not ratified design.
Legend: yellow cells are for you to fill in after running each test (W7 baseline result, CTMM result, notes). The Pass column computes itself.
# | W7 open threat | Memo § | Closure category | CTMM mechanism | Mechanism status | Test oracle (what must happen) | Coverage method | Evidence class | W7 baseline result | CTMM result | Pass? | Notes / next action
1 | Revocation impossible | 4.3.5 | Closable now | GT slot version numbers — O(1) revocation | Ratified | Make N copies of a GT; revoke once. Every copy faults; revoke cost independent of N (FPGA cycle counter). | Sweep N = 1…max c-list size; cycle count must be flat | Proven (by test + invariant) |  |  |  | Recommended first test spec.
2 | Untrusted machine code: forged references | 4.3.3 | Closable now | Hardware-checked GT on every reference | Ratified | Forged bit patterns, data-as-capability, out-of-bounds offsets all fault. | Exhaustive over typ / tag / version fields; structured fuzz over offsets | Proven (exhaustive) |  |  |  | Strongest claim vs W7.
3 | Reflection: debugger breaks all boundaries | 4.3.4 | Closable now | Dev/prod split — two root lumps differing by one c-list entry | Ratified | Reachability closure from prod root contains no debug authority. | Graph closure over all c-lists reachable from prod root | Proven (proof by closure) |  |  |  | Stronger than a test.
4 | Ambient authority: ports, load, interaction-environment, dynamic-wind | 3.4 | Closable now | Womb-and-cord birth; Enter-only outsider permission | Ratified | Newborn lump's reachable authority equals exactly what the womb granted. | Authority census at birth for every lump type | Proven (by test + invariant)
5 | Authentication / sealing not supported | 2.3.3, 4.1 | Closable after spec fix | Seals; Abstract GTs (typ=11), non-portable by construction | Ratified (spec conflict) | Unseal without unsealer faults; exporting an Abstract GT across namespaces faults. | Exhaustive over namespace pairs | Modelled until typ conflict resolved |  |  |  | Resolve the §0 vs §6 typ contradiction first.
6 | Quotas: one program exhausts memory | 4.3.5 | Closable with bounds | Per-namespace tracing GC; eviction as pressure relief | Ratified | Hostile namespace allocates unboundedly; neighbours see no failure and latency within stated bound. | Stress test across namespace counts | Modelled (needs numeric bound) |  |  |  | Define the latency bound.
7 | Persistence outside protection | 4.3.5 | Closable with bounds | LUMP lifecycle | Ratified | Evict, reload, compare authority: identical; no file-system path involved. | Round-trip every lump type | Modelled
8 | Preemption / termination; engine response depends on nesting depth | 4.3.1 | Open in CTMM | Not on file | Unknown | Callee loops or nests deeply; caller regains control in bounded time independent of depth. | Sweep nesting depth; response time must be flat | Speculative |  |  |  | Hardest gap; critics probe first. Define mechanism.
9 | Continuations invoked multiple times | 4.3.2 | Open in CTMM | Not on file | Unknown | Callee retains its return path and invokes it twice; second call faults. | All return paths | Speculative |  |  |  | Is return one-shot in the CTMM?
10 | Concurrency: shared cells | Footnote 3 | Open in CTMM | Not on file | Unknown | Racing writers to a shared lump: serialized or faulted. | Randomised interleavings | Speculative
11 | Accountability: who acts for whom | 4.3.5 | Partial | Identity / seal architecture; pioneering window | Ratified (partial) | Every invocation attributable to originating womb. | Trace every call chain in test suite | Modelled |  |  |  | Needs precise definition of 'accountable'.
12 | Schroeder problem: callee remembers/leaks inputs | 4.2.1 | Not closable by test | Enter-only; no outward write authority at entry | Inferred | Reachability: callee holds no outward write authority at entry. | Closure over callee c-list | Proven for explicit channels; covert channels open |  |  |  | State plainly that timing/covert channels remain.
13 | Undecidability of 'might divulge input' | 2.2.6 | Not closable by test | — | n/a | — | — | Mathematical limit |  |  |  | CTMM moves the line, does not remove it.
14 | Trust in administrator / manufacturing chain | 2.2.5 | Not closable by test | Artix-7 silicon + bitstream toolchain | n/a | — | Reproducible bitstreams narrow, do not close | Out of test scope
15 | Distribution / remote invocation | 4.3.5 | Out of scope | — | n/a | — | — | Out of scope |  |  |  | Declare explicitly rather than leave implied.
Note on L5: PASS = W7 baseline attack succeeds AND the same attack on the CTMM faults at the predicted point.

## Summary
Summary by closure category
Closure category | Threats | Passed | Not run
Closable now
Closable after spec fix
Closable with bounds
Partial
Open in CTMM
Not closable by test
Out of scope
Total

## Method
Test method
What closes a threat | A test only shows one attack failed. A threat is closed by: (1) a named CTMM mechanism, (2) an invariant true by construction, (3) an adversarial test plus a coverage argument. Small typ/tag fields make exhaustive coverage feasible.
Step 1 — Baseline | Write the attack as a W7 / Scheme 48 program and show it succeeds.
Step 2 — Port | Translate the same attack into a CTMM lump, using the telecom running example (dot.phone.Dial).
Step 3 — Oracle | State the expected fault: which fault, at which instruction, within what cycle bound (FPGA cycle counter).
Step 4 — Coverage | Run exhaustively or by structured fuzzing over the relevant field: GT typ, version, offset, or c-list slot.
Pass criterion | W7 baseline attack succeeds AND the CTMM version faults at the predicted point.
Evidence classes | Proven = invariant + exhaustive test or closure proof. Modelled = mechanism specified, bound or spec still to fix. Speculative = no mechanism on file.
Source | Rees, J. 'A Security Kernel Based on the Lambda-Calculus', MIT AI Memo 1564, 1996. https://dspace.mit.edu/handle/1721.1/5944

## Completeness
ID | Area | Requirement / issue | Scope | Priority | Status | Owner | Dependencies | Current evidence / gap | Closure criterion / next action | Source reference | Reviewed date | Evidence / result link | Due date
W7-01 | W7 security | Revocation impossible | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Make N copies of a GT; revoke once. Every copy faults; revoke cost independent of N (FPGA cycle counter). Coverage: Sweep N = 1…max c-list size; cycle count must be flat | Workbook: Threat Map row 6; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-02 | W7 security | Untrusted machine code: forged references | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Forged bit patterns, data-as-capability, out-of-bounds offsets all fault. Coverage: Exhaustive over typ / tag / version fields; structured fuzz over offsets | Workbook: Threat Map row 7; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-03 | W7 security | Reflection: debugger breaks all boundaries | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Reachability closure from prod root contains no debug authority. Coverage: Graph closure over all c-lists reachable from prod root | Workbook: Threat Map row 8; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-04 | W7 security | Ambient authority: ports, load, interaction-environment, dynamic-wind | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Newborn lump's reachable authority equals exactly what the womb granted. Coverage: Authority census at birth for every lump type | Workbook: Threat Map row 9; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-05 | W7 security | Authentication / sealing not supported | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Unseal without unsealer faults; exporting an Abstract GT across namespaces faults. Coverage: Exhaustive over namespace pairs | Workbook: Threat Map row 10; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-06 | W7 security | Quotas: one program exhausts memory | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Hostile namespace allocates unboundedly; neighbours see no failure and latency within stated bound. Coverage: Stress test across namespace counts | Workbook: Threat Map row 11; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-07 | W7 security | Persistence outside protection | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Evict, reload, compare authority: identical; no file-system path involved. Coverage: Round-trip every lump type | Workbook: Threat Map row 12; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-08 | W7 security | Preemption / termination; engine response depends on nesting depth | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Callee loops or nests deeply; caller regains control in bounded time independent of depth. Coverage: Sweep nesting depth; response time must be flat | Workbook: Threat Map row 13; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-09 | W7 security | Continuations invoked multiple times | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Callee retains its return path and invokes it twice; second call faults. Coverage: All return paths | Workbook: Threat Map row 14; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-10 | W7 security | Concurrency: shared cells | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Racing writers to a shared lump: serialized or faulted. Coverage: Randomised interleavings | Workbook: Threat Map row 15; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-11 | W7 security | Accountability: who acts for whom | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Every invocation attributable to originating womb. Coverage: Trace every call chain in test suite | Workbook: Threat Map row 16; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-12 | W7 security | Schroeder problem: callee remembers/leaks inputs | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | Reachability: callee holds no outward write authority at entry. Coverage: Closure over callee c-list | Workbook: Threat Map row 17; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-13 | W7 security | Undecidability of 'might divulge input' | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | — Coverage: — | Workbook: Threat Map row 18; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-14 | W7 security | Trust in administrator / manufacturing chain | Phase 1 assurance | High | Not run | Unassigned |  | Original workbook claim, not independently qualified. See original row. | — Coverage: Reproducible bitstreams narrow, do not close | Workbook: Threat Map row 19; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
W7-15 | W7 security | Distribution / remote invocation | Phase 2 | High | Out of scope | Unassigned |  | Original workbook claim, not independently qualified. See original row. | — Coverage: — | Workbook: Threat Map row 20; docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
H01 | Hardware acceptance | Every ordinary opcode, all register positions, DR0 and aliased inputs; ALU 0, ±1, signed extrema, carry/borrow; shifts 0/1/31. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Exact result, NZCV and preserved state against the core reference; close its oracle gaps before declaring full coverage. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H02 | Hardware acceptance | All 16 NZCV combinations × every defined condition; false-condition invalid operands, CR13, NULL/EXACT and malformed encodings. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Skip has no operand effect/fault; only next fetch and independent watchdog behavior remain. Reserved NV is not silently assumed. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H03 | Hardware acceptance | Each approved CALL form; both signs; row magnitudes 0/31, method 0/127 or 0/2047; LOAD/SAVE/DREAD/DWRITE ±1023, BRANCH ±262143. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Hand-checked packed word and latched operands; correct byte/word conversion; no wrap/truncation. Zero, last-valid and first-invalid effective indices. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H04 | Hardware acceptance | BFEXT/BFINS width 1/31 and invalid 0; positions 0/31, crossing bit 31, DR underflow/overflow, shared source/destination. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Exact result and flags or fault before destination mutation; preserve unaffected insertion bits. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H05 | Hardware acceptance | Direct/indexed CALL methods 0, first/last public, private zero and outside table/code; nested calls, RETURN mask 0/all/each bit, root/empty/corrupt continuation; LAMBDA. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Correct E authority, c-list/code reconstruction, continuation and mask; no hidden snapshot or unchecked fast return. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-05: docs/reviews/phase1-baseline/README.md
H06 | Hardware acceptance | GT classes, permissions, domains, bounds, stale generation; mutate each integrity-covered bit and F/G separately; denied/allowed MMIO. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Required access fails before unauthorized effects; full 9-bit equality, unchanged versions and exact integrity formula. No inferred permission from slot membership. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H07 | Hardware acceptance | NULL literal/nonzero/B variants; EXACT equal/unequal non-NULL, one/both NULL; raw NULL modifier 31; condition skips. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Exact approved NZCV or pre-mutation fault at the TPERM instruction. Equality never proves validity. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H08 | Hardware acceptance | Valid, malformed and suspended/root Thread contexts; permission-bearing operand GT; unused invalid c-list row then use it. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Context failures 0x1D, separate operand permission failure 0x1E; no eager entire-c-list scan; each restored CR GT passes mLoad. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H09 | Hardware acceptance | CHANGE self/helper/other; SWITCH both legal spellings, both signs, CR15.M absent; invalid Namespace/entry; CR13 operands. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Save/load order, unchanged ordinary CR15, shared SWITCH authority, fixed slot-2 entry, no CR13 writes; no target execution on failure. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-05: docs/reviews/phase1-baseline/README.md
H10 | Hardware acceptance | Cold configuration, warm reset, authorized marker, same word at wrong PC/from RAM, replay after acceptance/fault, malformed final CALL CR0. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | One-shot 0x27000001 only at immutable ROM site; no extra CR12.M; ROM fetch authority ends only on successful final CALL. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-04: docs/reviews/phase1-baseline/README.md
H11 | Hardware acceptance | Boot pair match, slot-1 mismatch, slot-2 mismatch after CR15 load, pair equal to itself but not bitstream; ordinary versus guarded handoff. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | VERSION with correct slot; no target activation, retry or rollback; ordinary entry version 0 versus guarded expected version. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-04: docs/reviews/phase1-baseline/README.md
H12 | Hardware acceptance | Default and configured Namespace capacity, first/last/outside slot and word, all fixed service slots, maximum intended allocation. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Ascending four-word entries; 256-slot default/limit 1023; slots 0/1/2/8/9/14/15; whole Phase 1 footprint fits half actual FPGA memory. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-04: docs/reviews/phase1-baseline/README.md
H13 | Hardware acceptance | All eight valid watchdog controls; power-on then warm reset with exemption on/off; each selector change while running. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Initial 0x5; controls retained across reset, elapsed count not retained; selector alone never extends current interval; readback is programmed selection. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H14 | Hardware acceptance | Every duration; instruction retirement, CALL/RETURN loops, stalls, self/helper CHANGE and SWITCH; completion before/at/after deadline. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Ungated elapsed time; only successful pre-deadline transfer renews; expiry wins equality, code 0x1F; no CR13/IRQ action. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H15 | Hardware acceptance | Exemption enter/exit, combined selector+exit (including 0x6), repeated non-exempt writes; every reserved control bit. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Fresh same-write duration on exit; repeated 0 does not renew; reserved bits read zero, writes wholly reject with 0x0B without stopping time. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H16 | Hardware acceptance | Exemption/selector update at expiry; instruction fault at expiry; incoming mLoad failure at renewal. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Whole control rejection at expiry; instruction fault wins reporting but not containment; failed transfer never renews. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H17 | Hardware acceptance | Expiry before/on/after program-write acceptance, delayed completion, partial multiwrite instruction and failed outgoing save. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Stop admission immediately; at most one accepted write completes within measured bound; no remaining instruction writes, retry, rollback or recovery write before completion. Failed validated save is not reported successful. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
H18 | Hardware acceptance | HARDFAULT 0xF7000000, retired opcodes, wrong-context reset marker, bad fetch/entry; recovery that changes visible PC. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | First fault code/location and pre-recovery state captured; no HALT substitution, speculative retirement or proof/private-state leakage. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-05: docs/reviews/phase1-baseline/README.md
H19 | Hardware acceptance | Behavioral, emitted RTL, mapped model and board replay of the same fixture. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Compare committed registers/flags/memory/faults, not internal cycle counts except deadline/completion bounds. No forced X values or stale model accepted. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-06: docs/reviews/phase1-baseline/README.md
H20 | Hardware acceptance | Exact build cold/warm reboot, repeated handoffs and fault/recovery trials; memory/ROM initialization and retained controls. | Phase 1 hardware | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Repeatable outcomes tied to bundle/input hashes, board identity, clock, logs and observed completion; no prior-run telemetry counted as new evidence. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-06: docs/reviews/phase1-baseline/README.md
S01 | Software acceptance | One IDE/several CMs; network T/local GT binding and virtual objects. Direct CM-to-CM, multiple IDEs and the two-Namespaces-on-one-FPGA networking test remain Phase 2. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
S02 | Software acceptance | Explicit loading; working Mint, pkverify and controlled nstab. Create/Replace/Destroy for application Abstractions, Threads, LS c-lists and RW data; no Mint MMIO/Namespace creation; growth estimates are not measured allocations. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
S03 | Software acceptance | Per-operation/target PassKey GT plus separate 128-bit proof; validate before EXACT; Genesis-only setup, sharing and revokers; reusable-until-revoked; pair-only revocation. Negative cases include missing proof, NULL/equal invalid GTs, stale/revoked and insufficient authority. SAVE identifies the GT-side detection point, not a completed proof mechanism. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
S04 | Software acceptance | Single-scope LAMBDA alone references NSRW-GT; one exclusive non-yielding slot update; verify/prepare before writes, publish only after confirmed writes. Reject resident/active Thread/code/c-list replacement or destruction before mutation. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
S05 | Software acceptance | First issue 0; release advances without wrap; reuse retained version; 510→511 permanently retires; stale issued GTs fault; full block zeroed before reuse; size-class pool tracking. Software enforces allocation policy; hardware never increments. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
S06 | Software acceptance | Retained boot-pair values 0…510 per half; unchanged builds retain them; explicitly changed configuration provisions matching bitstream/GTs. CR0-only policy defaults retain, saved per configuration; alternate new-guard choice does not bypass validation. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
S07 | Software acceptance | Exact-artifact static HARDFAULT attribution; otherwise raw origin. No private proof logging. Full release evidence includes simulator/RTL/exact board; any Genesis override records scope explicitly and is never a pass. | Phase 1 software | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. |  | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
CM-A | CM objectives | Defined shared tuples per Thread | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Multiple authorized methods read/update one defined record across calls and returns; other records are unchanged; another Thread gains no implicit access; stale allocation references are rejected. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-B | CM objectives | Protected continuation versus heap data | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Authorized heap operations cannot modify protected frames or ownership metadata; a defined self-capture preserves execution ownership and records the specified continuation without CHANGE. Callable capture remains gated on its contract. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-C | CM objectives | Retained checkpoints and rollback | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Verify one-shot restore, copied checkpoint identity, reset invalidation/retention, and fail-closed interruption. Restore only the declared data scope and never historical ownership/consumption metadata. Gated on checkpoint implementation. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-D | CM objectives | Capability-controlled MMIO | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Test authorized device access, absent/insufficient authority, invalid bounds and malformed register writes. Rejected operations produce no unauthorized device effect; heap rollback does not replay MMIO. Separate emulator evidence from physical-device evidence. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-E | CM objectives | Thread execution ownership | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Test distinct-target exclusion, continuous self-target ownership, pause/step preservation, and all indicator writers. Verify saved NIA cannot supply ownership. Gated on running-bit approval and implementation. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-F | CM objectives | Hardware watchdog containment | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | With exemption explicitly disabled, test documented elapsed-time expiry during loops/deep calls and accepted-write completion before protected capture. Test exemption authority separately; do not substitute a caller-return oracle for the specified hard fault. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-G | CM objectives | IDE/runtime tuple agreement | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Round-trip JSON through the same tuple layout used by callable methods; preserve omitted fields; reject stale confirmations and invalid edits without partial writes or protected-state changes. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
CM-H | CM objectives | Exact artifact/build attribution | Phase 1 assurance | High | Not run | Unassigned | See source gate dependencies | Defined objective; full acceptance not established by this tracker. | Attach the actual LUMP/configuration and implementation identities to results; hardware claims identify the tested bitstream and board. Mark differences from simulator-only coverage. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17 | BASE-09: docs/reviews/phase1-baseline/README.md
PERF-1 | Performance | Register arithmetic and branches, e.g. IADD/ISUB plus loop control | Phase 1 measurement | High | Not run | Unassigned | See source gate dependencies | Estimate only: Approximately 2 cycles/instruction / 25 million | Measure correct successful retirements for five one-second windows; retain exact build and trace mode. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
PERF-2 | Performance | Authorized local DREAD/DWRITE loops, with readback verification | Phase 1 measurement | High | Not run | Unassigned | See source gate dependencies | Estimate only: Approximately 4–5 cycles/instruction / 10–12.5 million | Measure correct successful retirements for five one-second windows; retain exact build and trace mode. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
PERF-3 | Performance | Fixed, declared mix of arithmetic, memory and capability/control instructions | Phase 1 measurement | High | Not run | Unassigned | See source gate dependencies | Estimate only: Assumed average 10 cycles/instruction / 5 million | Measure correct successful retirements for five one-second windows; retain exact build and trace mode. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
PERF-4 | Performance | Capability/control-heavy workload, including legal CALL/RETURN and CHANGE/SWITCH paths | Phase 1 measurement | High | Not run | Unassigned | See source gate dependencies | Estimate only: Illustrative average 25–50 cycles/instruction, not a timing claim for each opcode / 1–2 million | Measure correct successful retirements for five one-second windows; retain exact build and trace mode. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
PERF-5 | Performance | Trace-limited execution with one 12-byte packet per retired instruction | Phase 1 measurement | High | Not run | Unassigned | See source gate dependencies | Estimate only: 57,600 baud, 8N1, 120 serial bits/instruction / Approximately 480 maximum | Measure correct successful retirements for five one-second windows; retain exact build and trace mode. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
PERF-6 | Performance | Trace-limited execution with three 12-byte packets per retired instruction | Phase 1 measurement | High | Not run | Unassigned | See source gate dependencies | Estimate only: 57,600 baud, 8N1, 360 serial bits/instruction / Approximately 160 maximum | Measure correct successful retirements for five one-second windows; retain exact build and trace mode. | docs/phase-1/W7-plus-plus-test-objectives.md | 2026-10-17
G1 | Mint gates | G1 — Legal Lambda/ABI/results | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S02 Lambda location jump vs inline JS; S03 continuation/frame/keep-mask differences; no demonstrated internal label X or CR result path | Prefer an existing legal same-artifact X binding plus validated private result-cell LOAD. Otherwise specify smallest architectural change; do not fabricate CRs, make a separate service, or enable old fused opcodes / Engineering trace and same-byte cross-layer tests first. Explicit architectural/provisioning approval if new subobject authority, aliases or continuation semantics are required. Accept exact proposed ABI only after this | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G2 | Mint gates | G2 — Original requester | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S03 protected caller E exists, not a proven service-facing authenticated hierarchy API | Prefer bounded read-only context attestation using existing trusted frame validation. Alternative new narrowly scoped context interface; reject caller strings, Owner bits and host callStack / Demonstrate legal authority and hierarchy mapping across Mint→PkVerify. Approve any new interface rather than broad Thread/NSRW access | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G3 | Mint gates | G3 — All live return dependencies | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S03 protected STO outside heap; no complete authoritative cross-Thread scanner found | Prefer validated bounded traversal of all live/suspended contexts under exclusion; alternative protected fully maintained dependency index / Engineering coverage of every frame/context lifecycle and corruption case. Approve interface if protected state is inaccessible; never narrow to current CR14/CR6 or all outstanding GTs | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G4 | Mint gates | G4 — Whole-update envelope | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S06 per-instruction busy; S07 M6/raw UART/reset and RAM priority; readback alone insufficient | First prove bounded existing admission/observer exclusion. If impossible, propose minimal interlock/reset containment or explicitly enforceable operational constraints. Prefer no new engine, but never weaken safety to avoid hardware / Engineering reachability and accepted-write latency evidence. Explicit approval for new hardware or restrictions; software gate separate from bitstream milestone | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G5 | Mint gates | G5 — Durable custody and anti-rollback | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S10 ordinary transactions/fsync are not a vault; Q54 needs atomic record/pool/counter and trustworthy boot restore | Dedicated private transactional store and separate keys; external monotonic revision anchor vs Genesis-verified latest-state procedure. Recommend independent anchor where available / Select custody/backup/latest-state mechanism and actual durability boundary, prove crash cuts and corruption/rollback rejection. No permission to lose pool entries or resume calls | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G6 | Mint gates | G6 — Protected provisioning/administration | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S09 verified HTTPS option but HTTP default and plaintext UART; board secure endpoint/key anchor unestablished | Authenticated confidential end-to-end path recommended; alternative explicit physical-isolation custody model only with evidence. Neither is a runtime Forge transport yet / Approve trust anchors/key custody, authenticated Genesis authorization and board receipt protocol; demonstrate secret-safe boot/debug/reset and runtime store exchange | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G7 | Mint gates | G7 — Identity/type/layout/allocator binding | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S01 Boot.Namespace role vs S11 Boot.NS seed; Q06 assigned-Owner policy vs legacy Abstract users; free/retired entry representation and virtualGT unresolved | Bind Boot to exact approved configuration self-entry, not new name. Configuration-scoped incarnation registry proposed; local T===GT. Reject virtual/non-memory objects until explicit binding exists. Typed validators and retained slot-history records / Engineering exact packing/allocator/zeroing fixtures and resource measurement. Approve identity-lifecycle/compatibility changes and final capacities; do not reopen initial empty targets or change residency | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
G8 | Mint gates | G8 — Diagnostic and release evidence | Phase 1 software | High | Open | Unassigned | See source gate dependencies | S04 HARDFAULT emission disabled; map verifier has empty production trust pins; old tests cover narrow paths | Reuse existing wider Phase 1 map/target qualification work, not a second standalone candidate investigation / Binding/key approval and exact-site provenance; JS/RTL/generated/exact-build/physical acceptance separately recorded. Any Genesis override must name missing evidence and scope | docs/reviews/mint-phase1/open-issues.md | 2026-10-17
SPEC-01 | Specification | Approved Master ISA and acceptance structure | Phase 1 assurance | High | Complete | Unassigned |  | Documentation exists; does not imply implementation conformance. | Retain approved decisions and separate H01-H20 from S01-S07. | docs/phase-1/01-isa/instruction-set.md | 2026-10-17
SPEC-02 | Specification | Close remaining instruction oracles | Phase 1 assurance | High | Open | Unassigned |  | NV/reserved fields, shifts, TPERM, protected frames/Lambda and fault precedence remain explicit gaps. | Approve independent expected words, flags, effects and faults before full conformance claims. | docs/phase-1/01-isa/instruction-set.md | 2026-10-17
IDE-01 | IDE | Additive Amobea and Thread design workspace | Phase 1 assurance | High | Needs verification | Unassigned |  | Integrated views exist; integrated acceptance is not re-run here. | Verify navigation, retained drafts and no replacement of existing IDE tools. | simulator/amobea/README.md | 2026-10-17
IDE-02 | IDE | Safe editor save, revision and buffer ownership | Phase 1 assurance | High | Needs verification | Unassigned |  | Workflow snapshot reports editor-roundtrip failures; root cause/current reproducibility not established. | Reproduce isolated failures; verify create/edit/save, delayed responses, history and draft preservation. | simulator/test_editor_roundtrip.js | 2026-10-17
IDE-03 | IDE | Namespace editor persistence and boot selection | Phase 1 assurance | High | Complete | Unassigned |  | Verified: 35 extracted-route tests; 4 real isolated endpoint acceptance tests; browser cancellation/resident save-reload/stale-tab checks, then targeted passing boot and incomplete-design follow-up after exact-revision UI repair. Complete saved rows/layout/identity and protected hashes checked; all 1,280 live files byte-identical. No runtime integrity checks weakened. | Verify save/reload, resident selection and boot entry without silent layout/identity changes. | server/lumps/ns-state.json | 2026-10-17 | docs/reviews/phase1-baseline/namespace-authority-progress.md#final-closure-evidence; scripts/run_namespace_save_acceptance.py; tests/e2e/namespace_save_acceptance.spec.js
IDE-04 | IDE | Actionable diagnostics and executed-artifact freshness | Phase 1 assurance | High | Needs verification | Unassigned |  | Selected-file errors now distinguish unreadable and changed bytes and provide a corrective action. Integrated UI and executed-artifact freshness still need verification. | Show failed operation, actual reason, mutation state and corrective action; distinguish editor from executed bytes. | simulator/test_execution_identity.js | 2026-10-17 | docs/reviews/phase1-baseline/namespace-authority-progress.md
IDE-05 | IDE | Hardware controls and causal command acknowledgement | Phase 1 assurance | High | Needs verification | Unassigned |  | Control/relay implementation exists; snapshot alone does not prove requested board action. | Validate request-correlated acknowledgement, stale reconnect rejection, fault halt and simulator/board separation. | tests/server/test_wukong_command_delivery.py | 2026-10-17
IDE-06 | IDE | Reference and compiler capability documentation agreement | Phase 1 assurance | High | Needs verification | Unassigned |  | Workflow snapshot flags API-reference and capability-block checks; not freshly reproduced. | Reconcile approved ISA, compiler forms, reference search and examples; retain explicit historical distinctions. | docs/phase-1/01-isa/instruction-set.md | 2026-10-17 | BASE-08: docs/reviews/phase1-baseline/README.md
FUNC-01 | Missing functions | Authenticated original requester and live-use query | Phase 1 assurance | High | Blocked | Unassigned | G2; G3; G6 | No demonstrated legal service interface; protected frames do not grant software read authority. | Approve and implement bounded attestation/traversal; no host callStack or widened heap workaround. | docs/reviews/mint-phase1/context-feasibility.md | 2026-10-17
FUNC-02 | Missing functions | Same-scope Lambda entry and capability-result path | Phase 1 assurance | High | Blocked | Unassigned | G1; SPEC-02 | G1 finds entry/continuation mismatch and unproven result authority. | Resolve ISA contract; prove legal binding and result LOAD through real gates. | docs/reviews/mint-phase1/context-feasibility.md | 2026-10-17
FUNC-03 | Missing functions | Tuple allocation and callable record lifecycle | Phase 1 assurance | High | Needs verification | Unassigned |  | 58-word demonstration ABI and methods exist; not a new privacy mechanism. | Verify allocation, bounds, permission revocation, malformed text and release/reuse with separate Threads for isolation. | simulator/thread-heap-record.js | 2026-10-17
FUNC-04 | Missing functions | Dijkstra messages between isolated Threads | Phase 1 assurance | High | Open | Unassigned |  | Required communication direction; operational protocol/ABI is not demonstrated by the tuple lab. | Define and approve capability-authorized send/receive, ownership, lifetime and fault semantics; test delivery. | docs/phase-1/Amobea-V1.md | 2026-10-17
FUNC-05 | Missing functions | Continuation capture and one-shot checkpoint restore | Phase 1 assurance | High | Blocked | Unassigned |  | Design contract remains gated; external effects must not be replayed by heap rollback. | Approve capture/restore scope, consumption identity and reset rules; test reuse/copy rejection. | docs/phase-1/Amobea-V1.md | 2026-10-17
FUNC-06 | Missing functions | Protected Thread running ownership | Phase 1 assurance | High | Blocked | Unassigned |  | Live bit 13 remains proposed; saved-frame bit 13 is NIA, not ownership. | Approve placement and all writer/validator changes; prove every activation path and self-target behavior. | docs/phase-1/Amobea-V1.md | 2026-10-17
FUNC-07 | Missing functions | Reprogrammable startup breakout and application admission | Phase 1 assurance | High | Open | Unassigned |  | Startup diagnostics must allow open-ended checked handoff; not approval of live lazy loading. | Specify target-selection authority and stopped resident delivery/activation; separate Phase 2 networking. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
SEAL-01 | Seal storage | Define authoritative seal storage and lifetime | Phase 1 assurance | High | Open | Unassigned |  | Dedicated completeness item requested by Genesis; exact storage contract requires reconciliation, not an assumed missing implementation. | Specify which seals, algorithm/meaning, trusted writer, location, access, retention and version binding; distinguish hashes, integrity32 and secret proofs. | docs/reviews/mint-phase1/security.md | 2026-10-17
SEAL-02 | Seal storage | Bind seal to exact artifact and destination identity | Phase 1 assurance | High | Needs verification | Unassigned |  | Exact-byte checks retained independently of catalog status; pending bytes, changed files and immutable local derivatives tested. Full seal/replay/field coverage not established. | Reject tampering, stale/replayed seals and mismatched artifact/slot/generation; prove every covered field and permitted F/G mutation. | docs/reviews/mint-phase1/namespace-update.md | 2026-10-17 | BASE-03: docs/reviews/phase1-baseline/README.md; docs/reviews/phase1-baseline/namespace-authority-progress.md
SEAL-03 | Seal storage | Atomic seal/data publication and reset containment | Phase 1 assurance | High | Open | Unassigned |  | A successful checksum comparison does not prove exclusion or durable commit. | Inject interruptions between data/seal writes; no partial or stale authority usable after reset; no implicit retry/rollback. | docs/reviews/mint-phase1/namespace-update.md | 2026-10-17
SEAL-04 | Seal storage | Protected proof/key custody, backup and revocation | Phase 1 assurance | High | Blocked | Unassigned | G5; G6 | G5/G6 open; public seals must not be confused with secret 128-bit proofs. | Prove access isolation, confidential provisioning, atomic pool/ID/credential commit, anti-rollback and safe restoration. | docs/reviews/mint-phase1/persistence.md | 2026-10-17
SEAL-05 | Seal storage | Storage fault detection versus authenticity | Phase 1 assurance | High | Open | Unassigned |  | No verified sideband SECDED coverage established here; integrity32 and UART CRC are not ECC. | Record required storage fault coverage; any ECC design needs separate approval, preserves 32-bit GT and tests fault paths. | hardware/hw_types.py | 2026-10-17
SIM-01 | Simulator / ISA | Independent current-ISA encoding and operand conformance | Phase 1 assurance | High | Needs verification | Unassigned |  | Assembler workflow reports failure; simulator agreement alone is not an independent oracle. | Use hand-encoded vectors for all forms, bounds, conditions, retired encodings and CR13 restrictions. | docs/phase-1/01-isa/instruction-set.md | 2026-10-17 | BASE-01: docs/reviews/phase1-baseline/README.md; BASE-03: docs/reviews/phase1-baseline/README.md
SIM-02 | Simulator / ISA | CALL RETURN LAMBDA cross-layer compatibility | Phase 1 assurance | High | Blocked | Unassigned |  | Synthetic component evidence reproduces a Lambda mismatch; green gap probes are not conformance. | Same-byte simulator and RTL cases must match approved entry, continuation, frame and capability effects. | docs/reviews/mint-phase1/context-feasibility.md | 2026-10-17 | BASE-05: docs/reviews/phase1-baseline/README.md
SIM-03 | Simulator / ISA | CHANGE SWITCH boot and Namespace geometry | Phase 1 assurance | High | Needs verification | Unassigned |  | Fresh combined verification: resident addresses 1024/7872, complete body identity, Thread ranges, matching Step-2 placements and private simulation checks pass without xfail exemptions. This is image-generator evidence only; same-byte simulator/RTL instruction conformance remains unverified. | Compare current ISA and simulator/RTL using immutable fixture identities and exact initial state. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-04: docs/reviews/phase1-baseline/README.md; BASE-05: docs/reviews/phase1-baseline/README.md; docs/reviews/phase1-baseline/namespace-authority-progress.md#combined-post-merge-verification--17-october-2026
SIM-04 | Simulator / ISA | Watchdog and first-fault semantics | Phase 1 assurance | High | Needs verification | Unassigned |  | Elapsed board clocks cannot be inferred from browser step speed. | Validate fault precedence and pre-recovery state; separate logical simulator checks from timed RTL/board proof. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
SIM-05 | Simulator / ISA | Historical artifact adaptation provenance | Phase 1 assurance | High | Needs verification | Unassigned |  | Alice/Mallory fixtures adapt old code in isolated RAM; originals remain immutable. | Record exact original/adapted words and current ISA; never claim adapted runs qualify historical binary unchanged. | simulator/test_alice_mallory_lab.js | 2026-10-17 | BASE-07: docs/reviews/phase1-baseline/README.md
REL-01 | RTL / bitstream | Fresh exact-source build provenance | Phase 1 hardware | High | Open | Unassigned |  | Prior inspection found 22/39 recorded build inputs differ; this is not a new build verification. | Regenerate authorized exact inputs; verify hashes, ROM/configuration, timing, DRC and artifact sidecars. | docs/wukong-release-chain.md | 2026-10-17 | BASE-06: docs/reviews/phase1-baseline/README.md; BASE-09: docs/reviews/phase1-baseline/README.md
REL-02 | RTL / bitstream | Physical acceptance of exact release candidate | Phase 1 hardware | High | Not run | Unassigned | REL-01; H19; H20; separate hardware authorization | No physical Phase 1 acceptance performed for this tracker. | After separate authorization, run H19/H20 with exact board/build identity and retained raw observations. | docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-09: docs/reviews/phase1-baseline/README.md
REL-03 | RTL / bitstream | Resolve reported regression failures | Phase 1 hardware | High | Needs verification | Unassigned |  | Fresh combined merge verification: 190 passed, 2 failed; no skips/xfails. Admission/allocation/private simulation: 128 passes. Independent image suite: 62 passes, 2 migration failures (parent/explicit config). Historical migration copies device address 0x40000014 into resident NS[10]; generator correctly rejects out-of-RAM placement. Other regression groups remain open. | Isolate current failures, classify stale fixtures versus defects; record commands, output, identities and reruns. | scripts/run-all-tests.sh | 2026-10-17 | BASE-01: docs/reviews/phase1-baseline/README.md; BASE-03: docs/reviews/phase1-baseline/README.md; BASE-08: docs/reviews/phase1-baseline/README.md; docs/reviews/phase1-baseline/namespace-authority-progress.md; docs/reviews/phase1-baseline/namespace-authority-progress.md#combined-post-merge-verification--17-october-2026
RES-Boot.NS | Named abstractions | Boot.NS — Namespace foundation | Phase 1 software | High | Needs verification | Unassigned |  | Saved snapshot uses legacy slot-2 UART layout; approved Phase 1 entry layout must be reconciled before qualification. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
RES-Boot.Thread | Named abstractions | Boot.Thread — Initial context | Phase 1 software | High | Needs verification | Unassigned |  | Saved resident initial context; not evidence of exact-board Phase 1 acceptance. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
RES-Thread.2 | Named abstractions | Thread.2 — Additional context | Phase 1 software | High | Needs verification | Unassigned |  | Saved resident context; approved entry and cooperative handoff need exact-artifact qualification. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
RES-Thread.3 | Named abstractions | Thread.3 — Additional context | Phase 1 software | High | Needs verification | Unassigned |  | Saved resident context; approved entry and cooperative handoff need exact-artifact qualification. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17
RES-SelfTest | Named abstractions | SelfTest — Startup diagnostic | Phase 1 software | High | Needs verification | Unassigned |  | Saved resident startup diagnostic; discarded failure results can mask errors. Inspect branch and return-status evidence. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-02: docs/reviews/phase1-baseline/README.md; BASE-07: docs/reviews/phase1-baseline/README.md
RES-CapabilityTest | Named abstractions | CapabilityTest — Capability/cooperative test coordinator | Phase 1 software | High | Needs verification | Unassigned |  | Saved resident boot target/test coordinator; validate calls to SelfTest and WukongCallHome, returns and cooperative CHANGE. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-02: docs/reviews/phase1-baseline/README.md
RES-WukongCallHome | Named abstractions | WukongCallHome — Authorized UART reporting | Phase 1 software | High | Needs verification | Unassigned |  | Saved resident UART reporting routine. Receipt alone does not prove all tests passed, current bitstream or authenticated identity. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/phase-1/04-release/isa-to-fpga-alignment-plan.md | 2026-10-17 | BASE-02: docs/reviews/phase1-baseline/README.md
RES-ide.Mint | Named abstractions | ide.Mint — Object and credential service | Phase 1 software | High | Open | Unassigned | G1-G8 | 57-answer ledger and Genesis review established; G1-G8 open. First credential Create-only in Boot, with permanently empty Replace/Destroy targets. Absent from inspected saved Namespace. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/reviews/mint-phase1/open-issues.md | 2026-10-17
RES-ide.PkVerify | Named abstractions | ide.PkVerify — Exact-request PassKey verifier | Phase 1 software | High | Open | Unassigned | G2; G3; G6 | Designed exact-request verifier, not qualified operational service. Absent from inspected saved Namespace; protected context and provisioning still gated. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/reviews/mint-phase1/open-issues.md | 2026-10-17
RES-ide.NSTab | Named abstractions | ide.NSTab — Namespace table RW object | Phase 1 software | High | Open | Unassigned |  | Specified RW table object, not an executable helper. Only Mint's internal Lambda may hold its table access; absent from inspected saved Namespace. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | server/lumps/ns-state.json; docs/reviews/mint-phase1/open-issues.md | 2026-10-17
RES-ide.Alice | Named abstractions | ide.Alice — Authorized containment example | Phase 1 software | High | Needs verification | Unassigned |  | Merged isolated simulator fixtures cover own-tuple DWRITE/DREAD and adapted legacy scenarios; not a new run or board acceptance. Not a saved resident here. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | simulator/test_alice_mallory_lab.js; simulator/test_alice_mallory_tuple_lab.js | 2026-10-17
RES-ide.Mallory | Named abstractions | ide.Mallory — Adversarial containment example | Phase 1 software | High | Needs verification | Unassigned |  | Merged seven tuple scenarios include absent-capability denial, own-tuple positive control, foreign/range read/write denial and full 58-word Alice integrity. No new run or board proof. | Record exact artifact, approved destination/binding, resident footprint and simulator/RTL/board acceptance separately. | simulator/test_alice_mallory_lab.js; simulator/test_alice_mallory_tuple_lab.js | 2026-10-17
BASE-01 | Baseline audit | Assembler/compiler | Phase 1 assurance | High | Open | Unassigned | SIM-01; REL-03 | Confirmed dependency-initialization failure; not an ISA verdict. Existing assembler workflow throws TypeError: ChurchAssembler is not a constructor at compiler line 220. Fresh in-memory probe reproduces it with global assembler undefined; injecting the real constructor removes this exception (the sample still has one compile diagnostic). | Establish explicit Node/compiler dependency setup and regression coverage; rerun isolated assembler suite before interpreting encoding failures. Do not weaken retired-opcode diagnostics. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-02 | Baseline audit | Namespace authority | Phase 1 assurance | High | Needs verification | Unassigned | RES-SelfTest; RES-WukongCallHome; RES-CapabilityTest; IDE-03 | Runtime admission and R26 now validate exact Namespace-selected bytes without an active manifest-row requirement. Real admission passes with missing, archived and duplicate catalog entries. Further consumer/flow evidence remains. | Correct the test's requirement for an active manifest row and inspect consumers for equivalent catalog vetoes. Validate exact Namespace-selected bytes, identity, permissions, allocation and binding directly. A library/history index may locate files but cannot override approval. No catalog repair or reselection is required merely to satisfy this test. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md; docs/reviews/phase1-baseline/namespace-authority-progress.md
BASE-03 | Baseline audit | LUMP GT validator | Phase 1 assurance | High | Open | Unassigned | SIM-01; SEAL-02; REL-03 | Legacy-oracle conflict; affected binary validity not established. Four reported R22 failures use _gt_word0_violation, which declares bit 26 spare and rejects it. The test itself notes Abstract GT encodings use bits 26:25=11. The four reported cases are 04b2913d, 3b057bbb, Ethernet.1.b169bba4 and Ethernet.1.fc72b0e3. | Classify each rejected word by approved type and permissions; replace the obsolete blanket rule only under the current contract. Do not declare all four artifacts valid just because the old rule is wrong. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-04 | Baseline audit | Boot-image agreement | Phase 1 assurance | High | Open | Unassigned | SIM-03; H10; H11; H12 | Shared generator/fixture contract failure; root cause provisional. All 18 reported failures stop at mandatory NS slot 2 is zeroed; 8 other cases passed. Tests build synthetic Boot.Abstr fixtures in temporary directories; generator still requires legacy slots (0,1,2,3,4,5,6,10). Agreement is not reached in these failed cases. | Trace fixture selection, generation policy and validator mode in an isolated copy. Reconcile approved slot-2 entry versus legacy device/profile semantics; do not remove validation merely to pass tests. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-05 | Baseline audit | RTL boot/control | Phase 1 assurance | High | Needs verification | Unassigned | SIM-02; SIM-03; H05; H09; H18 | Unresolved fixture/implementation/oracle failures. Existing run: 8 failed, 46 passed. Failures cover SWITCH outcomes, delayed-fault issuer attribution, nested CALL/RETURN and saved-PC validation. No fresh RTL simulation was performed. | Capture instruction words and pre-fault state, verify approved fixture encodings, then replay minimal isolated cases. Keep implementation defects possible until evidence excludes them. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-06 | Baseline audit | Generated initialization | Phase 1 assurance | High | Open | Unassigned | REL-01; H19; H20 | Reported generated-artifact/source mismatch; not freshly recomputed. Existing guard: RTLIL init ROM 2693 entries versus Python source 2694; 1 failed, 25 passed in that suite. | Freeze source and approved image first; then regenerate and qualify exact outputs under separate authorization. Do not equate a one-entry count fix with a qualified bitstream. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-07 | Baseline audit | SelfTest freshness | Phase 1 assurance | High | Open | Unassigned | RES-SelfTest; SIM-05 | Reported source/entry-format drift, not observed execution failure. Selected SelfTest hash is intact. Existing freshness guard says instruction body MATCH, embedded text DIFFERENT, method-entry format DIFFERENT. The first failing command prevents the chained guard-test command from running. | Independently inspect actual CALL dispatch/decoder behavior for the exact selected artifact before proposing replacement. Preserve the selected bytes and distinguish source freshness from execution compatibility. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-08 | Baseline audit | API reference suite | Phase 1 assurance | High | Needs verification | Unassigned | IDE-06; REL-03 | Probable fixture/contract drift; not a fresh test result. Existing run fails in test_abs_saved_api.js: compiled method declarations unavailable. The fixture invokes _formatLumpApiDefinition('LED', []); failure occurs before the advertised reference comparison completes. | Supply authentic compiled metadata in the fixture, or establish why valid metadata is lost; retain fail-closed refusal to infer API from another LUMP. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md
BASE-09 | Baseline audit | Bitstream provenance | Phase 1 assurance | High | Open | Unassigned | REL-01; REL-02; CM-H | Confirmed current-source drift from recorded build. Fresh hash comparison finds 22 of 39 recorded input fingerprints differ from current files. The record's historical “verified” label is not qualification of today's source. | Freeze the candidate source/configuration; obtain matching generation, build/timing, artifact hashes and authorized physical evidence. Do not relabel the historical bitstream. | docs/reviews/phase1-baseline/README.md | 2026-10-17 | docs/reviews/phase1-baseline/README.md

## Progress
Phase 1 completeness — evidence-based tracking | Count / rate
Updated | 2026-10-17
Total tracked rows | 113
Open | 24
Blocked | 6
Not run | 56
Needs verification | 24
In progress | 0
Complete | 2
Failed | 0
Out of scope | 1
In-scope completion | 1.786%
Interpretation | Counts of different items; each item has one status. Row completion is not ISA/security coverage.
Area | Tracked | Complete items | Blocked items
CM objectives | 8 | 0 | 0
Hardware acceptance | 20 | 0 | 0
IDE | 6 | 1 | 0
Mint gates | 8 | 0 | 0
Missing functions | 7 | 0 | 4
Named abstractions | 12 | 0 | 0
Performance | 6 | 0 | 0
RTL / bitstream | 3 | 0 | 0
Seal storage | 5 | 0 | 1
Simulator / ISA | 5 | 0 | 1
Software acceptance | 7 | 0 | 0
Specification | 2 | 1 | 0
W7 security | 15 | 0 | 0
Baseline audit | 9 | 0 | 0

## Tracking guide
Rule | Meaning
Purpose | Expanded CTMM W7 completeness tracker; original Threat Map, Summary and Method retained without changed cells/formulas/styles.
Original claims | Original Ratified/Proven labels are supplied claims, not newly verified findings. Original Summary covers only the 15 threats; Progress covers the new register.
Complete | Closure criterion satisfied at its stated evidence level; cite dated reproducible evidence. Documentation completion is not hardware acceptance.
Needs verification | Implementation, reported merge or failure exists, but current end-to-end acceptance/root cause has not been verified here.
Open / Blocked | Open: work or decision remains. Blocked: prerequisite authority, contract or mechanism missing. Not run: defined objective with no qualifying run recorded.
No invented status | No new simulator, RTL or hardware runs were performed to populate this workbook; workflow snapshot failures are leads, not confirmed current defects.
Maintaining progress | Edit Completeness, assign Owner and Due date, add evidence, update Reviewed date and dependencies. Append rows within the Excel table; summaries cover rows 2–10000.
Evidence identity | Record exact source, fixture/artifact, build/board, command, date, outcome and exclusions. Never put credentials, keys, proofs or private records in this workbook.
Scope | Phase 1 hardware and software delivery are separate gates. Phase 2 networking remains out of scope. Proposed ECC and running-bit interfaces are not approved by this tracker.
Seal storage | Reconcile authoritative seal semantics/storage with existing implementations; distinguish authenticity seals, public integrity checks, secret proof custody and ECC.
Calculations | Excel/LibreOffice recalculates formulas on open. Python does not evaluate them. Completion percentage is unweighted row closure, not a security-confidence metric.
Source references | Repository-relative source paths describe where to find requirements; they are not portable public URLs or runtime test evidence.
Baseline audit | Nine root-cause groups. Workflow results are existing observations, not fresh reruns. Only the compiler dependency and read-only hash/binding probes were reproduced. See repository audit report.
Namespace authority | Genesis-approved Namespace selection is authoritative. A manifest may index library/history files, but missing, archived or duplicate catalog rows cannot veto independently verified selected bytes. BASE-02 tracks the competing test requirement, not a request to repair approved selections.

## Baseline audit
ID | Area | Classification / confidence | Observation | Next action | Related requirements
BASE-01 | Assembler/compiler | Confirmed dependency-initialization failure; not an ISA verdict | Existing assembler workflow throws TypeError: ChurchAssembler is not a constructor at compiler line 220. Fresh in-memory probe reproduces it with global assembler undefined; injecting the real constructor removes this exception (the sample still has one compile diagnostic). | Establish explicit Node/compiler dependency setup and regression coverage; rerun isolated assembler suite before interpreting encoding failures. Do not weaken retired-opcode diagnostics. | SIM-01; REL-03
BASE-02 | Namespace authority | Test imposes a competing manifest-authority requirement | Selected SelfTest has one active matching catalog row; selected WukongCallHome and CapabilityTest have zero. All three selected binary hashes match their files. Genesis confirms the approved Namespace list is authoritative; missing active catalog rows do not invalidate these selections. Hash agreement alone is not full execution qualification. Subsequent implementation: admission and R26 catalog veto removed; see docs/reviews/phase1-baseline/namespace-authority-progress.md | Verify remaining save/preview/image consumers against Namespace authority. Preserve exact-byte and allocation checks; no catalog repair or reselection merely for archive flags. | RES-SelfTest; RES-WukongCallHome; RES-CapabilityTest; IDE-03
BASE-03 | LUMP GT validator | Legacy-oracle conflict; affected binary validity not established | Four reported R22 failures use _gt_word0_violation, which declares bit 26 spare and rejects it. The test itself notes Abstract GT encodings use bits 26:25=11. The four reported cases are 04b2913d, 3b057bbb, Ethernet.1.b169bba4 and Ethernet.1.fc72b0e3. | Classify each rejected word by approved type and permissions; replace the obsolete blanket rule only under the current contract. Do not declare all four artifacts valid just because the old rule is wrong. | SIM-01; SEAL-02; REL-03
BASE-04 | Boot-image agreement | Shared generator/fixture contract failure; root cause provisional | All 18 reported failures stop at mandatory NS slot 2 is zeroed; 8 other cases passed. Tests build synthetic Boot.Abstr fixtures in temporary directories; generator still requires legacy slots (0,1,2,3,4,5,6,10). Agreement is not reached in these failed cases. | Trace fixture selection, generation policy and validator mode in an isolated copy. Reconcile approved slot-2 entry versus legacy device/profile semantics; do not remove validation merely to pass tests. | SIM-03; H10; H11; H12
BASE-05 | RTL boot/control | Unresolved fixture/implementation/oracle failures | Existing run: 8 failed, 46 passed. Failures cover SWITCH outcomes, delayed-fault issuer attribution, nested CALL/RETURN and saved-PC validation. No fresh RTL simulation was performed. | Capture instruction words and pre-fault state, verify approved fixture encodings, then replay minimal isolated cases. Keep implementation defects possible until evidence excludes them. | SIM-02; SIM-03; H05; H09; H18
BASE-06 | Generated initialization | Reported generated-artifact/source mismatch; not freshly recomputed | Existing guard: RTLIL init ROM 2693 entries versus Python source 2694; 1 failed, 25 passed in that suite. | Freeze source and approved image first; then regenerate and qualify exact outputs under separate authorization. Do not equate a one-entry count fix with a qualified bitstream. | REL-01; H19; H20
BASE-07 | SelfTest freshness | Reported source/entry-format drift, not observed execution failure | Selected SelfTest hash is intact. Existing freshness guard says instruction body MATCH, embedded text DIFFERENT, method-entry format DIFFERENT. The first failing command prevents the chained guard-test command from running. | Independently inspect actual CALL dispatch/decoder behavior for the exact selected artifact before proposing replacement. Preserve the selected bytes and distinguish source freshness from execution compatibility. | RES-SelfTest; SIM-05
BASE-08 | API reference suite | Probable fixture/contract drift; not a fresh test result | Existing run fails in test_abs_saved_api.js: compiled method declarations unavailable. The fixture invokes _formatLumpApiDefinition('LED', []); failure occurs before the advertised reference comparison completes. | Supply authentic compiled metadata in the fixture, or establish why valid metadata is lost; retain fail-closed refusal to infer API from another LUMP. | IDE-06; REL-03
BASE-09 | Bitstream provenance | Confirmed current-source drift from recorded build | Fresh hash comparison finds 22 of 39 recorded input fingerprints differ from current files. The record's historical “verified” label is not qualification of today's source. | Freeze the candidate source/configuration; obtain matching generation, build/timing, artifact hashes and authorized physical evidence. Do not relabel the historical bitstream. | REL-01; REL-02; CM-H